## UIAO-013 Review Record
UIAO-013 · UIAO MASTER PROJECT PLAN · WAVE 1 DOCUMENT REVIEW RECORD
Classification: Controlled ¦ Boundary: GCC-Moderate ¦ Doc Type: Reference ¦ Category: Project ¦ NIST: PL; PM; SA
Document ID |  | UIAO-013 |  |  | Review Date |  | 2026-06-15
Title |  | UIAO Master Project Plan |  |  | Reviewer |  | Michael Stratton
Doc Type |  | Reference |  |  | Review Cadence |  | Monthly
Category |  | Project |  |  | Previous Review |  | 2026-04-21 (May cycle SKIPPED — OVERDUE)
Version |  | 1.0.0 |  |  | Next Review Due |  | 2026-07-15
NIST Families |  | PL; PM; SA |  |  | Primary Reviewer Role |  | Compliance Officer + Owner
Tier at Review |  | CRITICAL (Rank #1 of 25 ¦ Score 187.0) |  |  | Action Items |  | 6 items across 5 sections
Verdict |  | CONDITIONAL PASS — UPDATE REQUIRED |  |  | Sections Reviewed |  | 10 of 10
SECTION REVIEW FINDINGS SUMMARY
✅ PASS · 4 |  |  | 🟡 UPDATE REQUIRED · 5 |  |  | 🔴 FLAG · 1 |  |  | Total Sections · 10
| § | Section Title | RC | Priority | Confidence | Reviewer Role | Finding | Finding Detail | Action Items | Evidence Pointer
| 1 | Document Header & Classification | ADM | Low | High | Owner | PASS | Header correctly marked Controlled / GCC-Moderate. Owner listed as Michael Stratton. Version 1.0.0. Dates match Master Index registry. No discrepancies. | None — section is clean. | UIAO Master Index row UIAO-013
| 2 | Executive Summary | ADM | Medium | High | Owner | UPDATE REQUIRED | Milestone completion percentages are from the April 2026 baseline and do not reflect June 2026 actuals. Wave 1 items listed as 'In Progress' are now complete per delivery records. | Update milestone percentages to June 2026 actuals; mark Wave 1 items COMPLETE. | UIAO-021 & UIAO-022 delivery confirmations
| 3 | Scope & System Boundary Definition | POL | High | High | Compliance Officer | PASS | System boundary aligns with current ATO boundary. GCC-Moderate classification is correctly scoped. No boundary expansion since last review. Verified against UIAO-009 §3. | None — boundary is accurate. | UIAO-009 §3; current ATO package
| 4 | Technical Specifications & Data | TECH | High | Medium | SME – Infrastructure | UPDATE REQUIRED | Two timeline entries reference Windows Server 2022 — correct baseline is WS2025 per UIAO-005. Sprint 3 toolchain lists PowerShell 5.1 — platform has migrated to PS 7.4. Git version target listed as 2.43; deployed version is 2.45.1. | 1) Replace WS2022 refs with WS2025. 2) Update PS target to 7.4. 3) Update Git to 2.45.1. | UIAO-005 §3 Prerequisites; UIAO-006 CLI Guide §2
| 5 | NIST Control Mapping Table | POL | High | High | Compliance Officer | PASS | Control families PL, PM, SA correctly mapped. PL-2, PM-1, SA-3 all listed as Implemented. No SP 800-53 Rev 5 deprecations since last review. Mapping is accurate and complete. | None — control mapping is current. | NIST SP 800-53 Rev 5 catalog; current SSP §13
| 6 | Gap Analysis / Findings | SEC | High | High | Compliance Officer | UPDATE REQUIRED | Two April 2026 open gaps are now remediated but still show OPEN: (1) Quarto pipeline gap — closed per UIAO-020. (2) AD read-only assessment tooling — closed per UIAO-008. New gap identified: UIAO-019 Governance Dashboard design complete but implementation not started. | 1) Mark Quarto gap CLOSED → UIAO-020. 2) Mark AD gap CLOSED → UIAO-008. 3) Add UIAO-019 implementation gap OPEN, target 2026-10-01. | UIAO-020 & UIAO-008 delivery records; UIAO-019 status log
| 7 | Decision Rationale / ADR Record | TECH | High | High | SME – Infrastructure | PASS | All four ADR entries (Git infra, IIS hosting, Active-Passive replication, Azure Arc) are recorded with correct decision dates. UIAO-004 cross-referenced correctly. No decisions superseded since April 2026. | None — ADR record is current. | UIAO-004 Architecture Decision Record §5
| 8 | Dependency & Integration Map | DRIFT | Medium | Medium | SME – Infrastructure | UPDATE REQUIRED | Four of seven integration touchpoints require update: (1) Quarto pipeline status still PLANNED — now ACTIVE. (2) UIAO-018 Azure Arc Policy Library dependency edge is missing from map. (3) UIAO-012 no longer blocks UIAO-011 — remove blocking arrow. (4) PowerShell module version ref stale (5.1 → 7.4). | 1) Update Quarto node to ACTIVE. 2) Add UIAO-018 edge. 3) Remove UIAO-012→UIAO-011 block. 4) Update PS version. | UIAO-020 integration status; UIAO-018 policy library status
| 9 | Cross-Document References & Links | DRIFT | Medium | High | Owner | FLAG | 11 of 14 cross-document references resolve correctly. 3 require action: (1) UIAO-003 link points to v0.9.0 draft URL — must point to v1.0.0 published path. (2) UIAO-019 referenced as 'v0.2' — document is now v1.0.0. (3) Internal SharePoint compliance tracker hyperlink returns 404. | 1) Fix UIAO-003 link → v1.0.0. 2) Update UIAO-019 ref → v1.0.0. 3) Repair / replace broken SharePoint compliance tracker link. MATERIAL: broken links are auditor-navigation failures. | UIAO document registry versions; SharePoint site admin
| 10 | Revision History | ADM | Low | High | Owner | UPDATE REQUIRED | Revision history ends at v1.0.0 (2026-04-21). May 2026 monthly review was not performed (document overdue). A new revision entry must be added for this June 2026 review. | Add v1.0.1 entry: date 2026-06-15, reviewer Michael Stratton, description 'Monthly review — milestone data, gap register, dependency map, and references updated.' | UIAO Master Index — Last Updated field
CONSOLIDATED ACTION ITEMS · ALL 6 MUST RESOLVE BEFORE 2026-07-15
# | Source § | Section | Priority | Action Required | Owner | Due | Status
1 | §2 | Executive Summary | High | Update milestone % to June 2026 actuals; mark Wave 1 items COMPLETE | Michael Stratton | 2026-06-22 | OPEN
2 | §4 | Technical Specifications | High | Replace WS2022→WS2025; update PS→7.4; update Git→2.45.1 | SME – Infrastructure | 2026-06-22 | OPEN
3 | §6 | Gap Analysis / Findings | High | Mark Quarto gap CLOSED (UIAO-020); mark AD gap CLOSED (UIAO-008); add UIAO-019 impl gap OPEN target 2026-10-01 | Michael Stratton | 2026-06-22 | OPEN
4 | §8 | Dependency & Integration Map | Medium | Quarto→ACTIVE; add UIAO-018 edge; remove UIAO-012→011 block; PS ref→7.4 | SME – Infrastructure | 2026-06-29 | OPEN
5 | §9 | Cross-Document References | High | Fix UIAO-003 link→v1.0.0; UIAO-019 ref→v1.0.0; repair SharePoint 404 link | Michael Stratton | 2026-06-22 | OPEN
6 | §10 | Revision History | Low | Add v1.0.1 entry: 2026-06-15, Michael Stratton, summary of accepted changes | Michael Stratton | 2026-06-22 | OPEN
REVIEW SIGN-OFF
Reviewed By |  | Michael Stratton |  |  | Review Date |  | 2026-06-15
Overall Verdict |  | CONDITIONAL PASS — UPDATE REQUIRED |  |  | Confidence |  | High — all 10 sections examined
Next Review Due |  | 2026-07-15 |  |  | Review Wave |  | Wave 1 — CRITICAL (25 days overdue)
Git Commit Target |  | docs/project/UIAO-013/reviews/UIAO-013-review-2026-06-15.xlsx |  |  | Registry Update |  | Update Last Updated → 2026-06-15; Next Review → 2026-07-15