## Priority Queue
UIAO DOCUMENTATION REVIEW — TASK 1.4: PRIORITY SCORING & REVIEW SCHEDULE
Classification: Controlled ¦ Boundary: GCC-Moderate ¦ Scored: 2026-06-15 ¦ Owner: Michael Stratton ¦ Total Docs: 25 ¦ Total Effort: 359.0 hrs
TIER LEGEND ▶ 🔴 CRITICAL = Overdue / immediate action 🟠 HIGH = ≥120 pts, action ≤30 days 🟡 MEDIUM = ≥75 pts 🟢 LOW = <75 pts │ Score = (Urgency + NIST Bonus + Section Risk) × Type Weight
Rank | Doc ID | Title | Doc Type | Category | NIST Families | Cadence | Next Review | Days Remaining | Priority Score | Tier | Urgency Score | NIST Bonus | Section Risk | Est. Effort (hrs) | Primary Reviewer
1 | UIAO-013 | UIAO Master Project Plan | Reference | Project | PL;PM;SA | Monthly | 2026-05-21 | OVERDUE 25d | 187 | CRITICAL | 150 | 3 | 17 | 14 | Compliance Officer
2 | UIAO-014 | UIAO Conditional Access Policy Library | Policy | Policy | AC;IA;CM | Quarterly | 2026-07-21 | +36 | 141.7 | HIGH | 70 | 10 | 29 | 19 | Compliance Officer
3 | UIAO-018 | UIAO Azure Arc Policy Library | Policy | Infrastructure | CM;SI;SC | Quarterly | 2026-07-21 | +36 | 140.4 | HIGH | 70 | 9 | 29 | 19 | Compliance Officer
4 | UIAO-021 | UIAO Disaster Recovery Playbook | Procedure | Operations | CP;IR;CM | Quarterly | 2026-07-21 | +36 | 118.8 | MEDIUM | 70 | 10 | 19 | 15 | SME – Infrastructure
5 | UIAO-008 | UIAO Read-Only AD Assessment Guide | Procedure | Assessment | CA;CM;RA | Quarterly | 2026-07-21 | +36 | 115.2 | MEDIUM | 70 | 7 | 19 | 15 | SME – Infrastructure
6 | UIAO-022 | UIAO Operations Runbook | Procedure | Operations | CM;SA;SI | Quarterly | 2026-07-21 | +36 | 114 | MEDIUM | 70 | 6 | 19 | 15 | SME – Infrastructure
7 | UIAO-009 | UIAO vs Microsoft Native Tools Gap Analysis | Reference | Assessment | CA;CM;PL;RA | Quarterly | 2026-07-21 | +36 | 104.5 | MEDIUM | 70 | 8 | 17 | 14 | Compliance Officer
8 | UIAO-024 | UIAO Compliance Mapping and Gap Analysis | Reference | Compliance | CA;PL;RA;CM | Quarterly | 2026-07-21 | +36 | 104.5 | MEDIUM | 70 | 8 | 17 | 14 | Compliance Officer
9 | UIAO-015 | UIAO Intune Policy Templates | Template | Policy | CM;SI;SC | Quarterly | 2026-07-21 | +36 | 95.5 | MEDIUM | 70 | 9 | 12 | 10 | SME – Infrastructure
10 | UIAO-007 | UIAO Active Directory Interaction Guide | Guidance | Assessment | CA;CM;RA | Quarterly | 2026-07-21 | +36 | 92 | MEDIUM | 70 | 7 | 15 | 13 | SME – Infrastructure
11 | UIAO-005 | UIAO Platform Server Build Guide | Procedure | Platform | CM;SA;SC | Semi-Annual | 2026-10-21 | +128 | 73.2 | LOW | 35 | 7 | 19 | 15 | SME – Infrastructure
12 | UIAO-019 | UIAO Governance Dashboard Design | Reference | Infrastructure | CA;CM;AU | Semi-Annual | 2026-10-21 | +128 | 64.9 | LOW | 35 | 7 | 17 | 14 | Compliance Officer
13 | UIAO-025 | UIAO Document Lifecycle Management Guide | Policy | Governance | CM;SA;PL | Annual | 2027-04-21 | +310 | 62.4 | LOW | 15 | 4 | 29 | 19 | Compliance Officer
14 | UIAO-006 | UIAO CLI and Operations Guide | Reference | Platform | CM;SA | Semi-Annual | 2026-10-21 | +128 | 60.5 | LOW | 35 | 3 | 17 | 14 | Compliance Officer
15 | UIAO-016 | UIAO PowerShell Module Reference | Reference | Reference | SA;CM | Semi-Annual | 2026-10-21 | +128 | 60.5 | LOW | 35 | 3 | 17 | 14 | Compliance Officer
16 | UIAO-010 | UIAO Identity Modernization Guide | Guidance | Modernization | AC;IA;CM | Semi-Annual | 2026-10-21 | +128 | 60 | LOW | 35 | 10 | 15 | 13 | SME – Infrastructure
17 | UIAO-012 | UIAO PKI Modernization Guide | Guidance | Modernization | IA;SC;CM | Semi-Annual | 2026-10-21 | +128 | 60 | LOW | 35 | 10 | 15 | 13 | SME – Infrastructure
18 | UIAO-011 | UIAO DNS Modernization Guide | Guidance | Modernization | CM;SC | Semi-Annual | 2026-10-21 | +128 | 56 | LOW | 35 | 6 | 15 | 13 | SME – Infrastructure
19 | UIAO-020 | UIAO Quarto Pipeline Integration Guide | Guidance | Operations | CM;SA | Semi-Annual | 2026-10-21 | +128 | 53 | LOW | 35 | 3 | 15 | 13 | SME – Infrastructure
20 | UIAO-023 | UIAO End User Training Guide | Guidance | Training | AT;CM | Semi-Annual | 2026-10-21 | +128 | 53 | LOW | 35 | 3 | 15 | 13 | SME – Infrastructure
21 | UIAO-017 | UIAO Active-Passive Git Replication Guide | Procedure | Infrastructure | CP;CM;SC | Annual | 2027-04-21 | +310 | 52.8 | LOW | 15 | 10 | 19 | 15 | SME – Infrastructure
22 | UIAO-002 | Git on Windows Server 2025 — Step-by-Step Guide | Procedure | Foundation | CM;SA | Annual | 2027-04-21 | +310 | 44.4 | LOW | 15 | 3 | 19 | 15 | SME – Infrastructure
23 | UIAO-001 | AD Computer Object Conversion Guide | Guidance | Foundation | AC;CM;IA;SI | Annual | 2027-04-21 | +310 | 43 | LOW | 15 | 13 | 15 | 13 | SME – Infrastructure
24 | UIAO-004 | UIAO Git Infrastructure — Architecture Decision Record | Reference | Foundation | CM;PL;SA | Annual | 2027-04-21 | +310 | 39.6 | LOW | 15 | 4 | 17 | 14 | Compliance Officer
25 | UIAO-003 | UIAO Git Server — Windows Server 2025 with IIS | Guidance | Foundation | CM;SA;SC | Annual | 2027-04-21 | +310 | 37 | LOW | 15 | 7 | 15 | 13 | SME – Infrastructure

## Review Schedule
REVIEW SCHEDULE — UIAO DOCUMENTATION REVIEW PROGRAM, PHASE 1
Scheduling baseline: 2026-06-15 ¦ All target dates are reviewer-action deadlines, not system review dates ¦ Review Window closes on Next Review Date
Wave | Doc ID | Title | Doc Type | Tier | Cadence | Next Review Date | Review Start | Target Complete | Est. Hours | Primary Reviewer | Status | Notes
▶ WAVE 1 — IMMEDIATE (CRITICAL / Overdue)
WAVE 1 — IMMEDIATE | UIAO-013 | UIAO Master Project Plan | Reference | CRITICAL | Monthly | 2026-05-21 | 2026-06-19 | 2026-06-22 | 14 | Compliance Officer | NOT STARTED
▶ WAVE 2 — URGENT (HIGH Priority ¦ Quarterly due 2026-07-21)
WAVE 2 — URGENT | UIAO-014 | UIAO Conditional Access Policy Library | Policy | HIGH | Quarterly | 2026-07-21 | 2026-07-03 | 2026-07-07 | 19 | Compliance Officer | NOT STARTED
WAVE 2 — URGENT | UIAO-018 | UIAO Azure Arc Policy Library | Policy | HIGH | Quarterly | 2026-07-21 | 2026-07-03 | 2026-07-07 | 19 | Compliance Officer | NOT STARTED
▶ WAVE 3 — QUARTERLY QUEUE (MEDIUM Priority ¦ Quarterly due 2026-07-21)
WAVE 3 — QUARTERLY QUEUE | UIAO-021 | UIAO Disaster Recovery Playbook | Procedure | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 15 | SME – Infrastructure | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-008 | UIAO Read-Only AD Assessment Guide | Procedure | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 15 | SME – Infrastructure | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-022 | UIAO Operations Runbook | Procedure | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 15 | SME – Infrastructure | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-009 | UIAO vs Microsoft Native Tools Gap Analysis | Reference | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 14 | Compliance Officer | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-024 | UIAO Compliance Mapping and Gap Analysis | Reference | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 14 | Compliance Officer | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-015 | UIAO Intune Policy Templates | Template | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 10 | SME – Infrastructure | NOT STARTED
WAVE 3 — QUARTERLY QUEUE | UIAO-007 | UIAO Active Directory Interaction Guide | Guidance | MEDIUM | Quarterly | 2026-07-21 | 2026-07-04 | 2026-07-07 | 13 | SME – Infrastructure | NOT STARTED
▶ WAVE 4 — SEMI-ANNUAL (LOW Priority ¦ Semi-Annual due 2026-10-21)
WAVE 4 — SEMI-ANNUAL | UIAO-005 | UIAO Platform Server Build Guide | Procedure | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 15 | SME – Infrastructure | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-019 | UIAO Governance Dashboard Design | Reference | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 14 | Compliance Officer | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-006 | UIAO CLI and Operations Guide | Reference | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 14 | Compliance Officer | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-016 | UIAO PowerShell Module Reference | Reference | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 14 | Compliance Officer | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-010 | UIAO Identity Modernization Guide | Guidance | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 13 | SME – Infrastructure | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-012 | UIAO PKI Modernization Guide | Guidance | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 13 | SME – Infrastructure | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-011 | UIAO DNS Modernization Guide | Guidance | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 13 | SME – Infrastructure | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-020 | UIAO Quarto Pipeline Integration Guide | Guidance | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 13 | SME – Infrastructure | NOT STARTED
WAVE 4 — SEMI-ANNUAL | UIAO-023 | UIAO End User Training Guide | Guidance | LOW | Semi-Annual | 2026-10-21 | 2026-09-18 | 2026-09-21 | 13 | SME – Infrastructure | NOT STARTED
▶ WAVE 5 — ANNUAL (LOW Priority ¦ Annual due 2027-04-21)
WAVE 5 — ANNUAL | UIAO-025 | UIAO Document Lifecycle Management Guide | Policy | LOW | Annual | 2027-04-21 | 2027-03-18 | 2027-03-22 | 19 | Compliance Officer | NOT STARTED
WAVE 5 — ANNUAL | UIAO-017 | UIAO Active-Passive Git Replication Guide | Procedure | LOW | Annual | 2027-04-21 | 2027-03-19 | 2027-03-22 | 15 | SME – Infrastructure | NOT STARTED
WAVE 5 — ANNUAL | UIAO-002 | Git on Windows Server 2025 — Step-by-Step Guide | Procedure | LOW | Annual | 2027-04-21 | 2027-03-19 | 2027-03-22 | 15 | SME – Infrastructure | NOT STARTED
WAVE 5 — ANNUAL | UIAO-001 | AD Computer Object Conversion Guide | Guidance | LOW | Annual | 2027-04-21 | 2027-03-19 | 2027-03-22 | 13 | SME – Infrastructure | NOT STARTED
WAVE 5 — ANNUAL | UIAO-004 | UIAO Git Infrastructure — Architecture Decision Record | Reference | LOW | Annual | 2027-04-21 | 2027-03-19 | 2027-03-22 | 14 | Compliance Officer | NOT STARTED
WAVE 5 — ANNUAL | UIAO-003 | UIAO Git Server — Windows Server 2025 with IIS | Guidance | LOW | Annual | 2027-04-21 | 2027-03-19 | 2027-03-22 | 13 | SME – Infrastructure | NOT STARTED

## Reviewer Workload
REVIEWER WORKLOAD ASSIGNMENT MATRIX
Generated: 2026-06-15 ¦ Hours derived from RC section counts × per-RC effort rates ¦ Does not include document coordination overhead
Doc ID | Title | Doc Type | Total Hrs | Michael Stratton | Compliance Officer | SME – Infrastructure | Wave | Tier | Notes
UIAO-013 | UIAO Master Project Plan | Reference | 14 | 3.5 | 6.5 | 4 | W1 | CRITICAL
UIAO-014 | UIAO Conditional Access Policy Library | Policy | 19 | 2 | 17 | 0 | W2 | HIGH
UIAO-018 | UIAO Azure Arc Policy Library | Policy | 19 | 2 | 17 | 0 | W2 | HIGH
UIAO-021 | UIAO Disaster Recovery Playbook | Procedure | 15 | 2.5 | 4.5 | 8 | W3 | MEDIUM
UIAO-008 | UIAO Read-Only AD Assessment Guide | Procedure | 15 | 2.5 | 4.5 | 8 | W3 | MEDIUM
UIAO-022 | UIAO Operations Runbook | Procedure | 15 | 2.5 | 4.5 | 8 | W3 | MEDIUM
UIAO-009 | UIAO vs Microsoft Native Tools Gap Analysis | Reference | 14 | 3.5 | 6.5 | 4 | W3 | MEDIUM
UIAO-024 | UIAO Compliance Mapping and Gap Analysis | Reference | 14 | 3.5 | 6.5 | 4 | W3 | MEDIUM
UIAO-015 | UIAO Intune Policy Templates | Template | 10 | 1 | 4 | 5 | W3 | MEDIUM
UIAO-007 | UIAO Active Directory Interaction Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W3 | MEDIUM
UIAO-005 | UIAO Platform Server Build Guide | Procedure | 15 | 2.5 | 4.5 | 8 | W4 | LOW
UIAO-019 | UIAO Governance Dashboard Design | Reference | 14 | 3.5 | 6.5 | 4 | W4 | LOW
UIAO-025 | UIAO Document Lifecycle Management Guide | Policy | 19 | 2 | 17 | 0 | W5 | LOW
UIAO-006 | UIAO CLI and Operations Guide | Reference | 14 | 3.5 | 6.5 | 4 | W4 | LOW
UIAO-016 | UIAO PowerShell Module Reference | Reference | 14 | 3.5 | 6.5 | 4 | W4 | LOW
UIAO-010 | UIAO Identity Modernization Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W4 | LOW
UIAO-012 | UIAO PKI Modernization Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W4 | LOW
UIAO-011 | UIAO DNS Modernization Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W4 | LOW
UIAO-020 | UIAO Quarto Pipeline Integration Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W4 | LOW
UIAO-023 | UIAO End User Training Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W4 | LOW
UIAO-017 | UIAO Active-Passive Git Replication Guide | Procedure | 15 | 2.5 | 4.5 | 8 | W5 | LOW
UIAO-002 | Git on Windows Server 2025 — Step-by-Step Guide | Procedure | 15 | 2.5 | 4.5 | 8 | W5 | LOW
UIAO-001 | AD Computer Object Conversion Guide | Guidance | 13 | 2.5 | 4.5 | 6 | W5 | LOW
UIAO-004 | UIAO Git Infrastructure — Architecture Decision Record | Reference | 14 | 3.5 | 6.5 | 4 | W5 | LOW
UIAO-003 | UIAO Git Server — Windows Server 2025 with IIS | Guidance | 13 | 2.5 | 4.5 | 6 | W5 | LOW
TOTAL | 25 Documents |  | 359 | 66.5 | 163.5 | 129

## Phase 1 Summary
UIAO DOCUMENTATION REVIEW PROGRAM — PHASE 1 COMPLETION SUMMARY
Phase 1 complete: Tasks 1.1 → 1.4 ¦ Baseline date: 2026-06-15 ¦ Owner: Michael Stratton ¦ Boundary: GCC-Moderate FedRAMP
Task | Title | Output Artifact | Status | Documents | Sections | Key Finding
1.1 | Build Master Document Index | UIAO_Master_Index_Task_1.1.xlsx | ✅ COMPLETE | 25 | — | All 25 UIAO documents inventoried; NIST control families, cadences, and owners assigned
1.2 | Classify Documents by Type | UIAO_Master_Index_Task_1.2.xlsx | ✅ COMPLETE | 25 | — | 5 types: Guidance×8, Reference×7, Procedure×6, Policy×3, Template×1; 3 flagged Needs Review
1.3 | Map Sections to Review Categories | UIAO_Master_Index_Task_1.3.xlsx | ✅ COMPLETE | 25 | 248 | 6 RC codes applied; 248 section–RC mappings with priority, reviewer role, and audit checklist item
1.4 | Priority Scoring & Review Schedule | UIAO_Master_Index_Task_1.4.xlsx | ✅ COMPLETE | 25 | 248 | 1 CRITICAL (overdue), 2 HIGH, 7 MEDIUM, 15 LOW; 5 review waves; 359 hrs total effort estimated
PHASE 1 KEY METRICS
Total Documents Inventoried |  | 25 |  | Total Section–RC Mappings |  | 248
CRITICAL (Overdue) |  | 1 |  | MEDIUM Priority |  | 7
HIGH Priority |  | 2 |  | LOW Priority |  | 15
Total Estimated Review Effort |  | 359.0 hrs |  | Overdue Documents |  | UIAO-013 (25 days)
Review Waves Defined |  | 5 |  | Earliest Wave Deadline |  | 2026-06-22 (Wave 1)
Primary Reviewer (SME) |  | SME – Infrastructure |  | Compliance Reviewer |  | Compliance Officer
Phase 2 Ready |  | YES — Begin document-level review |  | Next Action |  | Execute Wave 1: UIAO-013 immediately
5-WAVE REVIEW SCHEDULE SUMMARY
Wave | Name | Tier | Documents | Window | Est. Hrs | % of Total | Action Required
W1 | IMMEDIATE — CRITICAL | CRITICAL | 1 doc (UIAO-013) | 2026-06-16 → 2026-06-22 | 14.0 | 3.9% | Review and update UIAO-013 immediately; it is 25 days overdue
W2 | URGENT — HIGH | HIGH | 2 docs (UIAO-014, UIAO-018) | 2026-06-16 → 2026-07-07 | 38.0 | 10.6% | Begin review by 2026-06-16; must complete before quarterly deadline
W3 | QUARTERLY QUEUE — MEDIUM | MEDIUM | 7 docs | 2026-06-23 → 2026-07-07 | 96.0 | 26.7% | Coordinate SME and Compliance Officer availability by 2026-06-20
W4 | SEMI-ANNUAL — LOW | LOW | 9 docs | 2026-08-01 → 2026-09-21 | 211.0 (partial) | — | Schedule as bandwidth permits; must complete before 2026-10-21
W5 | ANNUAL — LOW | LOW | 6 docs | 2027-01-01 → 2027-03-21 | (see W4) | — | Begin Q1 2027; coordinate with annual review cycle